## Instructions
TOOL
SUMMER PLANNING CALENDAR WORKBOOK
For more information on the importance of comprehensive planning and tips for an effective year-round planning process, review the Summer Planning Calendar Companion Guide in the Summer Learning Toolkit.
INTRODUCTION
The Summer Planning Calendar supports school districts and their partners to take a year-round, comprehensive approach to planning academic summer programs. It is comprised of two complementary resources: the Workbook and the Companion Guide.
The Summer Planning Calendar is based on the approaches of a set of districts and their partners and draws best practices from their experiences as well as research and recommendations from the RAND Corporation and technical assistance and guidance provided by the Wallace Foundation.
The Workbook enables users to customize their own calendars based on the specific schedules, resources, and needs of their districts. While the tool is designed for district-run summer programs, content is likely relevant and applicable to others interested in running high-quality summer programs, including school-based summer leaders and other city agencies, intermediaries, and nonprofit organizations.
The Companion Guide provides background on the importance of each planning category in the Workbook and tips for getting started.
HOW THE PLANNING CALENDAR IS ORGANIZED
The Workbook organizes tasks and activities into 14 planning categories that represent the major areas of work required to design and deliver comprehensive summer programs. The categories are:
1. Planning and Management
2. Program Budget
3. Continuous Improvement Process
4. Facilities
5. Student Recruitment
6. Staffing and Hiring
7. Curriculum
8. Enrichment
9. Professional Development
10. Site Operations and Culture
11. Schedules and Rosters
12. Transportation
13. Meals
14. Supplies
The Workbook can be viewed two ways:
12-Month Summary: a snapshot of all key activities, organized by planning category, with a month-by-month calendar to indicate when activities are likely to occur throughout the year.
By Planning Category: a more detailed timeline of key activities and tasks, organized by planning category.
The last tab in the Workbook creates a sortable task list by compiling information from each planning category tab into one list. Instructions to create a chronological task list are included at the top of the Sortable Task List tab.
KEY TERMS
KEY ACTIVITIES – primary activities that often involve multiple stakeholders and span several months
TASKS – steps to complete the key activities that often occur within one or two months
RELATED TIPS – general guidance or recommendations
Throughout the calendar, tasks are identified as either:
ESSENTIAL – these tasks are critical for implementation and should be included in any district’s summer program planning; OR
RECOMMENDED – these tasks raise the bar of quality in program design and planning and are appropriate for districts with some experience operating a summer program. Many of these tasks align with RAND’s evidence and recommendations from its formative evaluation of a set of districts that had several years of experience operating summer programs.
HOW TO USE THE SUMMER PLANNING CALENDAR WORKBOOK
After a quick walkthrough of the Workbook and Companion Guide, follow these recommended steps to customize a planning calendar for your district:
1. Go through the Workbook one planning category at a time, reviewing the activities and tasks. Then, review the corresponding guidance in the Companion Guide.
2. Eliminate Workbook activities or tasks that do not apply to your program model. For example, transportation-related activities specific to planning bussing routes will not be applicable to programs where students walk or take public transit.
3. Estimate the start date of your program, and set the timeline and deadlines to match your schedule.
4. Determine who needs to be engaged in planning to make key decisions and execute tasks involved in program design and implementation for each planning category.
5. Identify which decisions, key activities, or tasks should be managed at the district level and which should be managed at the site level.
6. Designate general roles and responsibilities for planning team members.
7. Begin filling in the Workbook with your planning details (see below).
8. Throughout the year, add other tasks deemed necessary to your planning process that are not included in the Workbook.
9. Sort the Sortable Task List regularly to reflect up-to-date changes and progress.
10. Consider other ways you can use the Workbook to customize tools to support your planning process. For example, use the chronological task list to create a 12-Month Summary to reflect your planning process. Or, use stop-light color-coding to emphasize the status of planning tasks.
The Workbook is designed to help you plan in alignment with best practices and track progress throughout your planning process. Each planning category includes a spreadsheet for you to complete and update regularly throughout your summer planning process. Populate the following information for each task:
COLUMN A: ESSENTIAL VS. RECOMMENDED – the template includes recommendations on whether the task is Essential or Recommended for your planning process; if necessary, change the cell values to reflect your planning process using E for Essential or R for Recommended.
COLUMN B: KEY ACTIVITIES AND TASKS – the template includes recommended activities and tasks for your planning process – no input required.
COLUMN C: RECOMMENDED TIMELINE – the template includes recommended month(s) the task should occur – no input required.
COLUMN D: OUR TIMELINE – month(s) the task should occur in your program.
COLUMN E: WHO'S RESPONSIBLE – staff responsible for managing the task to completion.
COLUMN F: APPROVAL REQUIRED (Y/N)? – indicate if approval from district leadership is required for task completion by selecting an option from the dropdown menu. To add or change the approval options, scroll down below the Workbook table. You may edit the existing options or add to the list in the GREEN cells only.
COLUMN G: IF APPROVAL REQUIRED, BY WHOM? – staff responsible for final approval, if applicable.
COLUMN H: DEADLINE – target deadline for completion.
COLUMN I: STATUS – select a status from the dropdown menu to track progress on a task. To add or change the status options, scroll down below the Workbook table. You may edit the existing options or add to the list in the GREEN cells only.
COLUMN J: DATE COMPLETED – date of task completion.
COLUMN K: NOTES - Planning Dependencies, Challenges, or Delays – critical dependencies between planning categories and/or activities that influence planning timeline or deadlines; challenges or delays important to note for planning future programs.
REFER TO THE SUMMER PLANNING CALENDAR COMPANION GUIDE FOR ADDITIONAL GUIDANCE ON USING THIS WORKBOOK AND LINKS TO RESEARCH ON DESIGNING AND IMPLEMENTING A HIGH-QUALITY SUMMER PROGRAM

## 12 Month Summary
SUMMER PLANNING CALENDAR WORKBOOK
12-MONTH SUMMARY
PLANNING |  | RECOMMENDED PLANNING TIMELINE
CATEGORY | KEY ACTIVITIES | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG
Planning and Management | Outline cross-departmental leadership structure for planning | bar: RECOMMENDED PLANNING TIMELINE SEP to RECOMMENDED PLANNING TIMELINE OCT
Determine planning process and timeline | bar: RECOMMENDED PLANNING TIMELINE NOV to RECOMMENDED PLANNING TIMELINE DEC; RECOMMENDED PLANNING TIMELINE AUG
Facilitate regular planning meetings | bar: RECOMMENDED PLANNING TIMELINE JAN to RECOMMENDED PLANNING TIMELINE AUG
Continuous Improvement Process | Develop new or refine existing evaluation plan
Use data to inform instruction and program development
Execute evaluation
Program Budget | Prepare budget for summer program | bar: RECOMMENDED PLANNING TIMELINE OCT to RECOMMENDED PLANNING TIMELINE JAN
Plan for program sustainability | bar: RECOMMENDED PLANNING TIMELINE NOV to RECOMMENDED PLANNING TIMELINE APR
Manage and reconcile budget regularly | bar: RECOMMENDED PLANNING TIMELINE FEB to RECOMMENDED PLANNING TIMELINE APR; RECOMMENDED PLANNING TIMELINE AUG
Facilities | Identify sites for summer program
Prepare sites for program implementation
Student Recruitment | Develop a marketing and recruitment plan | bar: RECOMMENDED PLANNING TIMELINE OCT to RECOMMENDED PLANNING TIMELINE NOV
Prepare student identification and recruitment process and materials | bar: RECOMMENDED PLANNING TIMELINE OCT to RECOMMENDED PLANNING TIMELINE DEC
Execute recruitment | bar: RECOMMENDED PLANNING TIMELINE FEB to RECOMMENDED PLANNING TIMELINE MAY
Notify parents of enrollment status | bar: RECOMMENDED PLANNING TIMELINE MAR to RECOMMENDED PLANNING TIMELINE JUN
Reach out and engage families and students for retention | bar: RECOMMENDED PLANNING TIMELINE JUN to RECOMMENDED PLANNING TIMELINE AUG
Staffing and Hiring | Determine staffing needs and hiring timeline
Recruit or select and hire site leads
Recruit or select and hire seasonal central office staff
Recruit or select and hire teachers
Recruit or select and hire other essential staff
Curriculum | Select, identify, or develop curriculum | bar: RECOMMENDED PLANNING TIMELINE OCT to RECOMMENDED PLANNING TIMELINE JAN
Develop new or revise existing pacing guides and lesson plans | bar: RECOMMENDED PLANNING TIMELINE JAN to RECOMMENDED PLANNING TIMELINE MAR
Identify curriculum materials needs and order supplies | bar: RECOMMENDED PLANNING TIMELINE FEB to RECOMMENDED PLANNING TIMELINE MAR
Organize and deliver curriculum materials | bar: RECOMMENDED PLANNING TIMELINE MAY
Enrichment | Recruit or select and contract with enrichment partners, providers, or staff
Plan for quality enrichment
Professional Development | Plan professional development | bar: RECOMMENDED PLANNING TIMELINE NOV to RECOMMENDED PLANNING TIMELINE APR
Implement professional development | bar: RECOMMENDED PLANNING TIMELINE MAY to RECOMMENDED PLANNING TIMELINE JUN
Site Operations and Culture Policies and Procedures | Define program culture and operating policies and procedures
Prepare site mangement procedures
Schedules and Rosters | Develop program schedule | bar: RECOMMENDED PLANNING TIMELINE NOV
Develop and share site schedules | bar: RECOMMENDED PLANNING TIMELINE JAN to RECOMMENDED PLANNING TIMELINE APR
Develop and share class schedules | bar: RECOMMENDED PLANNING TIMELINE MAY to RECOMMENDED PLANNING TIMELINE JUN
Transportation | Coordinate transportation
Execute transportation
Meals | Coordinate food service across sites | bar: RECOMMENDED PLANNING TIMELINE NOV to RECOMMENDED PLANNING TIMELINE FEB
Coordinate and execute food service at each program site | bar: RECOMMENDED PLANNING TIMELINE MAR to RECOMMENDED PLANNING TIMELINE JUN
Supplies | Determine supply needs
Order, organize, and deliver supplies to sites
Manage supplies during and after the program

## Planning & Management
SUMMER PLANNING CALENDAR WORKBOOK
PLANNING AND MANGEMENT
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 27.
Why planning and management is important
Through its New Vision for Summer School Network, the National Summer Learning Association promotes a vision that “school districts and schools use the summer as part of a 12-month plan for learning to accelerate their priorities around student and teacher success.”
Central to this vision is a core principle to embed summer learning into the district’s year-round operations.
Aligned with this vision, RAND studied district integration efforts in three districts – Dallas, Pittsburgh, and Rochester. Summer learning leaders reported that embedding summer into district year-round priorities and operations resulted in improved program quality, increased efficiencies, movement toward program sustainability, and a better connection between summer and year-round programming.
RAND’s Making Summer Last: Integrating Summer Programming into Core District Principles and Operations report highlights critical steps to move toward integration, including garnering buy in from district leadership and across departments, allocating resources in the district’s annual budget, taking a year-round approach to planning, including summer planning responsibilities in key positions, and setting expectations for program sustainability.
How to get started
Prioritize building your planning team, defining a governance structure, and developing systems to manage and support program planning.
Planning tips and recommendations
✓ To garner district support for integration, build awareness among chief executives, the board, and departmental leaders about how the summer program helps improve academic achievement and moves the district toward specific goals. Districts used several approaches to build awareness among leaders, including sharing student testimonials during cabinet meetings, facilitating summer site visits with leaders, and engaging staff in student outreach and recruitment.
✓ Build a central office leadership team that includes representation from key departments and cabinet-level officials, including: Human Resources, Payroll, Curriculum and Instruction, Data Assessment, Student Support Services, Transportation, Technology/Information Systems, Facilities, and Meals.
✓ Hire or identify a summer program lead with authority to lead program planning and engage and manage members of the leadership team.
✓ Begin regular planning meetings in the fall, and meet at least monthly.
✓ Beginning in the late winter, include budget reviews as a regular agenda item.
✓ Beginning in late winter / early spring, engage site-level leadership (including principals) in planning meetings.
✓ Meet regularly during the summer program to monitor program execution and address program-wide and site-level needs.
✓ Discuss whether changes are needed to planning team structure or responsibilities during end-of-summer debriefs.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS† | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Outline cross-departmental leadership structure for planning |  | Sep-Oct
E | Confirm staff lead to oversee summer program planning | Sep
E | Define roles and responsibilities for district, site leadership, and partner staff related to program planning and implementation | Sep
E | Develop system to coordinate and track planning progress | Sep
E | Determine members of planning team | Oct
Determine planning process and timeline |  | Nov-Dec, Aug
R | Develop monthly planning schedule with key tasks, monthly deadlines, and who's responsible (including district, site leadership, and partner staff) | Nov
R | Identify planning expectations (responsibilities, meeting schedule) for all staff to include in job descriptions | Dec
R | Identify planning expectations (responsibilities, meeting schedule) for all partners to include in partner agreements | Dec
R | Collect feedback on the delineation of roles and responsibilities for planning, program management, and evaluation during annual debrief with district staff, site leadership, and partners | Aug
Facilitate regular planning meetings |  | Jan-Aug
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Continuous Improvement
SUMMER PLANNING CALENDAR WORKBOOK
CONTINUOUS IMPROVEMENT PROCESS
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 23.
Why a continuous improvement process is important
Summer program continuous improvement processes vary greatly and are based on a number of factors, such as a district’s year-round evaluation processes, priorities and capacities for measuring student outcomes and teacher performance, and systems for gathering stakeholder feedback.
In Getting to Work on Summer Learning, 2nd ed., RAND found that districts that collected and used data to drive program reflection and and planning with program and district leadership made changes that resulted in substantial improvement to the effectiveness and cost effectiveness of the program. In particular, RAND recommends building a process to collect and discuss data focused on program attendance, instructional practices, use of time, and site climate. Improving overall program quality can increase student engagement and ultimately yield better student outcomes.
How to get started
Begin by setting goals for program quality and student outcomes. Next, develop assessments to measure both, and determine the processes you will use for data collection, analysis, and sharing. Consider which processes will work best with your district’s year-round evaluation and improvement approach. Many summer programs collect the spring and fall benchmark test scores of summer program participants to assess the impact of the summer program on reading and math. Other programs administer pre/post tests during the summer program or conduct program observations to collect data.
Planning tips and recommendations
✓ Include in your comprehensive evaluation plan ways to assess and monitor if the program is being implemented as designed across sites and if the program is achieving its goals for student outcomes. These may Include site visit or observation protocols and assessments completed by students, teachers, and/or parents.
✓ Disaggregate and analyze data on high-attenders, low-attenders, and no-shows to understand the relationship between attendance and student outcomes and to inform recruitment, budgeting, and facilities planning for the next year.
Conduct debriefs with planning teams to discuss data and stakeholder feedback and identify improvement goals for the following summer.
✓ Share end-of-summer results with all stakeholders including district and school leadership, program partners and funders, program staff, enrichment providers, and families. Provide opportunities for stakeholders to discuss results and provide feedback that informs planning for the following summer.
✓ At the end of the summer, reflect on the professional development plan to identify strengths and areas for improvement based on program outcomes.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Develop new or refine existing program evaluation plan |  | Sep-Feb
R | Begin to discuss the evaluation plan for next summer | Sep
R | Define or update program goals and expected outcomes | Oct
R | Finalize the program evaluation plan, including systems and processes for data collection, analysis, dissemination, and application | Nov
E | Determine data sharing requirements and include relevant language in partner MOUs | Nov
E | Select or develop assessments to measure program quality and student outcomes (e.g. youth academic and social emotional skills; instructional quality; effectiveness of professional development; and participant, staff, and stakeholder satisfaction, etc.) | Dec
E | Develop mechanism to monitor fidelity of curriculum and enrichment implementation | Feb
Use data to inform instruction and program development |  | Oct, May-Jun
R | Share end-of-summer data from previous summer with program stakeholders | Oct
E | Conduct debrief with planning team and examine data from previous summer to identify improvements for next summer | Oct
R | Collect spring reading and math data to form class groupings by ability levels | May
R | Provide data in an easily accessible format to classroom teachers | Jun
Execute evaluation |  | Sep, Apr-Aug
R | Collect and analyze fall student testing data and compare to previous spring testing data to assess student and program outcomes from the previous summer program | Sep
R | Administer pre-assessments according to schedule (e.g. spring school-year assessments or in-program skills pre-assessment) | Apr
E | Collect and analyze student daily attendance data | Jun-Aug
E | Observe academic and enrichment instruction and provide feedback to staff during and at the end of the program | Jun-Jul
R | Conduct end-of-program assessment (if applicable) | Jul
R | Conduct focus groups to gather feedback from key stakeholders including students, families, staff, and partners | Jul-Aug
E | Analyze collected data | Aug
E | Develop list of students that met promotion criteria (if applicable) | Aug
R | Begin to prepare end-of-summer data reports on enrollment, attendance, program quality, student outcomes, and satisfaction surveys (staff, student, families, and partners) for various stakeholder groups, including principals | Aug
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Program Budget
SUMMER PLANNING CALENDAR WORKBOOK
PROGRAM BUDGET
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 20.
Why the program budget is important
Designating sufficient resources to implement your summer plan with high quality and fidelity to program design is critical to its success. Careful resource planning and allocation can also ensure that you are spending precious funds on the most important elements of your program.
How to get started
Begin by developing your budget with estimated costs for site operations and administrative overhead. Then, compare cost projections against existing funds to identify funding needs, and develop a plan to secure additional funds. Next, develop your internal budget management systems and processes. Keep in mind that while funding models for summer programs can range in complexity–some districts use a single source of restricted or unrestricted funds to support program operations while others complement district funds with foundation grants and public funding–the budget development process takes time and involves multiple iterations and negotiations between district and program leaders. Plan ahead and communicate often.
Planning tips and recommendations
✓ Explore a variety of funding sources and resources to support the program, including school district general funds, other city funding, Title I, 21st Century Community Learning Centers, IDEA-B, Title II, AmeriCorps, private philanthropy, corporate and individual donors, and participant fees.
✓ Base your staffing estimates on your historic "no-show" rate. If you don't have one, assume a 15% no-show rate.
✓ Additionally, plan for attrition within projected enrollment to more accurately project expenses related to staff, materials/supplies, facilities, and transportation for field trips. Use historic average daily attendance rates (ADA) for budget estimates; if you don’t have one, assume a 75% ADA.
✓ Analyze expenses against the budget quarterly to identify funding gaps and adjust the budget as needed.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Prepare budget for the summer program |  | Oct-Apr
E | Estimate budget based on prior year budget and actual expenditures | Oct
R | Schedule regular meetings with finance or other administration to periodically review budgets | Nov
E | Determine primary costs for each site including personnel, facilities, meals, transportation, materials and supplies, and administrative and overhead costs | Dec
E | Discuss budget estimates with district leadership | Dec
E | Confirm existing federal, state, local, district, and philanthropic funds that will support the program | Jan
E | Identify revenue gaps and operating categories that require additional funding | Jan
E | Present draft budget to district leadership for approval | Jan
E | Confirm budget to operate each summer site and update budget draft | Feb
E | Engage the leadership planning team to review the updated draft budget | Mar
E | Finalize program budget | Apr
Plan for program sustainability |  | Jan-Apr
R | Identify potential funding sources to support program growth and sustainability | Jan-Mar
R | Prepare fundraising materials including case statements, proposals, budgets, impact data, etc. | Jan-Mar
R | Confirm new funding, update budgets and revenue sources, and develop plan for managing funding based on requirements | Apr
Manage and reconcile budget regularly |  | Feb-Mar, Aug
E | Develop payment process for enrichment partners and vendors | Feb
E | Develop process to manage and track expenditures against budget | Mar
E | Process final expenses and payments | Aug
E | Reconcile all expenditures against budget | Aug
E | Prepare financial reports for district/community leaders and program funders | Aug
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Facilities
SUMMER PLANNING CALENDAR WORKBOOK
FACILITIES
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 21.
Why facilities are important
Choosing the right sites for your program is based on several factors–the anticipated body of students, school feeder patterns, building capacity, planned capital improvements, and program needs for special spaces or equipment (e.g. technology, music, art, physical fitness, etc.). Early planning is critical to ensure smooth building operations, particularly at sites where summer leadership will be different than during the school year.
How to get started
Begin by developing a list of possible sites for the summer program, considering enrollment goals, neighborhoods where targeted students live, and adequacy of building assets based on program needs. Then meet with the facilities department to determine if any buildings may be scheduled for capital improvements in the summer.
Planning tips and recommendations
✓ Identify community-based programs that may target similar students for recruitment. Consider ways to differentiate services in marketing materials to enable families to select programs that best meet their needs and interests. Additionally, avoid selecting program sites in areas with high availability of community programs to minimize competition for program enrollment and attendance.
✓ Include room and equipment use as part of written agreement to ensure access to supply closets and necessary equipment such as copiers.
✓ Specify need for full building access in building permits/written agreements.
✓ Consider data on high-attenders, low-attenders, and no-shows from previous summers to inform facilities planning.
✓ Ensure sufficient custodial and grounds services are scheduled for the program months.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Identify sites for summer program |  | Oct-Jan
R | Develop a list of targeted sites to host summer programs | Oct
E | Meet with directors of facilities and custodial services to review building capacity and capital improvements or construction planned for the summer | Nov
E | Research city and school district summer permitting processes, if applicable | Nov
R | Create a preliminary projection of the number of students that will attend each site | Nov
E | Confirm dates for summer program based on school calendar and facilities availability | Nov
E | Confirm sites and available classrooms for summer program | Dec
E | Identify contacts for facilities, equipment, etc., at each site | Dec
R | Develop written agreement that describes how the sites will be used | Dec
E | Notify school-year principals of site selection and requirements for hosting summer program | Jan
E | Determine feeder patterns, if applicable | Jan
Prepare sites for program implementation |  | Feb-Mar, May
R | Conduct meetings between summer site principals and school-year principals to discuss facility needs, emergency plans, bus drop-off locations, etc. | Feb
E | Coordinate with the district (and/or city if appropriate) to ensure that school zones operate during the summer and that crossing guards are available at all locations | Mar
R | Conduct site walk-throughs | May
R | Develop safety plan for summer site principals to share with staff during professional development | May
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Student Recruitment
SUMMER PLANNING CALENDAR WORKBOOK
STUDENT RECRUITMENT
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 27.
Why student recruitment is important
As highlighted in Marketing Summer Learning to Parents and Students: Lessons from the National Summer Learning Project, getting the right students to register for your program, show up, and participate regularly is no easy feat.
It requires advanced planning, consistent outreach, targeted messages and compelling materials, and relationship-building between program staff and families. With guidance from Crosby Marketing Communications, a set of districts designed and implemented recruitment plans with great success–all exceeded their recruitment goals and reduced their no-show rates from previous summers.
How to get started
Begin by developing marketing and recruitment strategies. Consider the students you hope to engage and the different ways you can connect with them over the months leading up to the program. Set recruitment goals, a plan for outreach activities, and systems to measure the impact of your efforts.
Planning tips and recommendations
✓ Consider program goals and capacity when prioritizing students for recruitment.
✓ Build separate strategies and activities for connecting with students and parents/caregivers into your recruitment and outreach plans.
✓ Develop targeted recruitment and outreach strategies for students who attended regularly the previous summer versus those who did not show up or attend regularly.
✓ Use a variety of methods to connect with families including events, mailers (letters, postcards, program newsletter, flyers), robo calls, individualized teacher and principal outreach, and registration incentives.
✓ Set the registration deadline 2-3 months in advance of program start; enrollment numbers are critical for planning related to facilities, transportation, meals, supplies, etc.
✓ Ensure that communications emphasize that the program is not a drop-in program, and that attendance is expected.
✓ Programs often experience attendance dips on Fridays and after the Fourth of July weekend. Plan additional outreach strategies to ensure student retention throughout the program.
See the Summer Learning Recruitment Guide for more detailed tips and best practices.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Develop intentional marketing and recruitment strategies |  | Oct-Nov
R | Identify all audiences with whom you need to communicate (e.g. priority families and students for recruitment) | Oct
R | Identify strategies for successfully reaching each of your target audiences | Oct
R | Develop a timeline for all outreach and recruitment activities | Nov
R | Develop strategies to measure success | Nov
Prepare student identification and recruitment process and materials |  | Oct-Dec
E | Determine enrollment process | Oct
R | Develop student identification plan including eligibility requirements | Oct
E | Create engaging messaging | Nov
E | Develop enrollment and consent forms and translate materials into appropriate languages | Nov
R | Develop recruitment packages for staff who play an essential role in outreach and recruitment (e.g., registration and outreach materials for planned family communications, such as mailers, talking points for outreach calls, personalized outreach, etc.) | Nov
E | Train school staff (e.g. attendance clerks) on process to manage summer enrollment on site | Nov
E | Announce summer program dates | Nov
E | Equip messengers, including providing information on enrollment process to school principals | Dec
E | Update school website with summer program information | Dec
E | Send first communication home with information on registration process and deadline | Dec
Execute recruitment |  | Feb-May
E | Distribute registration materials to schools | Feb
E | Equip teachers or other designated recruitment specialists to conduct individualized outreach to eligible students and families | Mar
R | Begin registration | Mar
E | Facilitate phone calls to homes (robocalls or personalized) | Mar
R | Send second communication home with registration deadline reminder | Apr
E | Facilitate final reminder calls to families who have not registered yet (robocalls or personalized) | Apr
R | Utilize test results to identify students who will be mandated to attend summer school for grade promotion (if applicable) | Apr
E | Close registration | May
Notify parents of enrollment status |  | Mar-Jun
E | Send confirmation letters or postcards to families and students who enrolled, notifying them that their spot has been reserved | Mar-May
E | Maintain waiting list and notify parents of enrollment if applicable | Mar-Jun
E | Share behavior management policy, attendance expectations and incentives, and transportation schedule with students and families through pre-program mailer | May
R | Make final reminder calls to families immediately prior to the program launch | Jun
Outreach/engagement for retention |  | Jun-Aug
R | Call parents of registered students who have not shown up to remind them of the program | Jun
R | Send mid-program newsletter to families | Jul-Aug
R | Send notification or reminder about culminating event(s) to families | Jul
R | Send thank you letters to students and families | Aug
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Staffing & Hiring
SUMMER PLANNING CALENDAR WORKBOOK
STAFFING AND HIRING
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 25.
Why staffing and hiring are important
Among all aspects of planning and implementing a high-quality program, hiring the right staff can have the greatest impact on students’ overall experience in the program.
In Getting to Work on Summer Learning, 2nd ed., RAND found that teachers with strong content knowledge led classes that were more effective and engaging. Those teachers were able to draw on their experience and extend lessons from the curricula guide and use instructional practices that increased student engagement, deepened critical thinking, and ensured students understood the material.
RAND also found that teachers’ interactions with students, both in and out of the classroom, contributed significantly to the site climate. At sites with consistently positive site climate, researchers observed that “instructional and non-instructional staff members were kind to students and handled student misbehavior consistently and appropriately” throughout the day. It’s important to design a hiring process that will help you recruit highly motivated staff and teachers with appropriate subject-matter and grade-level experience.
How to get started
Begin by determining staffing needs for all key positions, including central office staff, site leaders, teachers and enrichment instructors, and other staff. Consider the roles and responsibilities and level of experience of required for each position. Develop a hiring process with a timeline for outreach, application submission and review, candidate interviews, and selection and placement. Work with your teacher's union to identify and recruit teachers with relevant grade-level and subject-matter expertise.
Planning tips and recommendations
✓ For districts that run multiple programs over the summer, first identify individual program staffing needs and hiring timelines. Then, compare across programs to streamline processes where possible.
✓ Include information about position duties and responsibilities, schedule, qualifications, and compensation in job descriptions.
✓ Gain buy-in from district leadership and teacher's union (if applicable) on time commitment and selection process for key positions.
✓ Work with teacher's union to identify and recruit teachers who have grade-level and subject-matter experience and previous experience with students, when possible.
✓ Set a deadline for hiring all staff that allows adequate time for professional development.
✓ Recruit principals of schools selected as summer sites to stay on as summer program site leads. This consistency in site leadership helps to ensure smooth program operations.
✓ Volunteers are a great way to increase program capacity. Identify operating and instructional needs that volunteers could support, and develop a process to recruit, train, and manage volunteers.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Determine staffing needs and hiring timeline |  | Oct-Feb
E | Define roles and responsibilities for site-level leadership related to program planning and implementation | Oct
E | Determine staffing needs for instructional positions and additional staff (e.g., classroom support, special education, nurses, custodians, etc.) | Nov
E | Determine hiring timeline for key positions including seasonal central office staff, site leadership, and teachers | Nov
E | Develop hiring and selection process for central office and site leadership, including application requirements and review rubric | Nov
E | Establish rate of pay for all summer program staff, including stipends for participation in professional development | Dec
E | Negotiate, update and sign union MOU that describes requirements of teachers and staff and the selection and hiring process | Dec
E | Coordinate hiring process with district staff who manage payroll and district hiring system | Jan
E | Develop hiring and selection process for teachers, including application requirements and review rubric | Jan
E | Develop hiring and selection process for additional staff including application requirements and review rubric | Feb
R | Develop process for tracking candidates and re-staffing position vacancies from waiting list (if/when need arises) | Feb
Recruit or identify and hire site leads |  | Dec-Feb
R | Identify and connect with staff from prior years who are encouraged to return | Dec
E | Develop job descriptions for site leads | Dec
E | Promote positions to eligible staff through district communication vehicles and personalized outreach | Jan
E | Review applications | Jan
E | Interview top candidates | Feb
E | Make offers and secure commitments | Feb
Recruit / identify and hire seasonal central office staff |  | Dec-Feb
R | Identify and connect with staff from prior years who are encouraged to return | Dec
E | Develop job descriptions for seasonal central office staff | Dec
E | Promote positions to eligible staff through district communication vehicles and personalized outreach | Jan
E | Review applications | Jan
E | Interview top candidates | Feb
E | Make offers and secure commitments | Feb
Recruit or select and hire teachers |  | Feb-Apr
R | Identify and connect with staff from prior years who are encouraged to return | Feb
E | Review teacher applications | Mar
E | Interview top candidates for teaching positions | Mar
E | Make selection decisions, including assigning teachers to schools, subject areas, and grade levels according to experience | Apr
E | Make offers and secure commitments from selected teachers | Apr
Recruit or select and hire other essential staff |  | Apr
E | Meet with district departments regarding additional staffing needs to identify positions and select staff (e.g. health services, food service, etc.) | Apr
E | Manage the process for confirming staff for these positions | Apr
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Curriculum
SUMMER PLANNING CALENDAR WORKBOOK
CURRICULUM
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 24.
Why curriculum is important
RAND found that adopting a common written curriculum for English language arts and mathematics that matches students’ academic needs and abilities is necessary for high-quality instruction. Such a curriculum provides teachers with the building blocks they need to be successful within the classroom and is essential for summer programs, which typically include very little time for teacher planning.
Selecting and modifying curriculum for use in summer learning programs is a major decision that creates both opportunities and challenges for program administrators and teachers, including how to maximize academic benefit in a short amount of time. Summer is also ripe with opportunity for exploration and is often used to implement new or innovative learning models.
Choosing the right curriculum is just the first step. RAND found that the right curriculum is necessary but not sufficient to ensure high-quality instruction. Programs must also support teachers by preparing lesson guides and equipping sites with the necessary materials and supplies.
How to get started
Begin by setting program goals for student outcomes. Then, determine if you need to find or develop new curriculum or if you can revise existing curriculum. Next, assess what materials you already have and what additional supplies or materials sites and teachers will need for quality instruction.
Planning tips and recommendations
✓ Consider alignment of summer curriculum with school-year curriculum.
✓ Develop pacing guides to reflect priorities for instructional time with suggested time allocations for various components of each day’s lesson, including scheduled transition times.
✓ Identify differentiation strategies within curricular materials to accommodate a minimum of two ability levels. Allow time for remediation.
✓ Ensure all materials necessary to train teachers in curriculum are available no later than one week prior to training.
✓ Ensure all curricula and related materials arrive onsite no later than one week prior to the program launch.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Select, identify, or develop curriculum |  | Oct-Jan
E | Set program goals for student outcomes | Oct
E | Identify staff to lead curriculum process | Nov
E | Request and provide curriculum team with first quarter reading and math data to assess student needs | Dec
R | Review commercially available and evidence-based curriculum and determine if curriculum aligned with program goals needs to be selected, developed, or revised | Dec
R | If program requires use of specific student assessment data for grouping or instructional purposes, schedule pre-assessment prior to program launch | Jan
E | If curriculum is computer-based, engage IT to identify technology needs and coordinate support leading up to and throughout the program | Jan
Develop new or revise existing pacing guides and lesson plans |  | Jan-Mar
R | Review student achievement data (winter benchmark) to determine student needs, including remediation | Jan
R | Draft or revise pacing guides and lesson plans to provide sufficient guidance to teachers | Feb
R | Finalize pacing guides and lesson plans to address district-specific decisions and needs related to groupings, differentiation, instruction for students with IEP's, etc. | Mar
Identify curriculum materials needs and order supplies |  | Feb-Mar
E | Complete an inventory of available curriculum materials and determine what is still needed for the program | Feb
E | Order additional materials and supplies | Mar
Organize and deliver curriculum materials |  | May
E | Print and prepare program-developed curriculum (e.g. lesson plans) | May
E | Organize all materials for easy pick-up and use | May
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Enrichment
SUMMER PLANNING CALENDAR WORKBOOK
ENRICHMENT
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 25.
Why enrichment is important
Researchers and practitioners alike consider offerring a range of fun activities to be an effective strategy for maximizing summer program participation. It is also an important way to reduce the income-based opportunity gap during the summer. RAND found that quality enrichment was key to creating fun and enjoyable days for students. High-quality enrichment classes included activities that were organized, engaging, and allowed for a majority of students to actively participate for the duration of the class period.
Using an RFP or application process can help ensure you recruit providers and instructors with aligned goals and a shared vision for high-quality implementation. A partner MOU clarifies roles and responsibilities and outlines planning and implementation expectations. Observing and providing feedback to enrichment instructors throughout the program can help you troubleshoot any challenges related to quality or alignment with program goals.
How to get started
Enrichment models can take many forms; your district may choose to partner with one organization to plan and lead all enrichment programming or engage multiple providers to lead different activities across the program. Some schools and community-based organizations jointly apply to collaboratively plan and run programs within a district. Begin by determining how enrichment programming will help you meet your overall program goals. Consider which of your existing partners or other high-quality providers in your community may be the right fit for your program.
Develop a process and timeline for recruitment that will bring in high-quality partners and instructors with the necessary experience and capacity. This may include an application that asks providers to describe their programming and how it aligns with your program’s vision for quality and student success.
Planning tips and recommendations
✓ Hold a pre-bid meeting with interested enrichment partners and/or instructors to provide an overview of the program, provider expectations, and the application and selection process.
✓ Include prompts related to activity goals, strategies for grouping students, and scope and sequence for the entire program in your request for proposals.
✓ In the winter, survey students on their interest in enrichment activities and field trips.
✓ Include enrichment providers in program planning beginning in late winter/early spring.
✓ Plan field trips that connect with program content and goals.
✓ Confirm field trips with host sites at least one month prior to the field trip date.
✓ Beginning in April, share program updates and information through regular emails with partners.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Recruit or select and contract with enrichment partners, providers, or staff |  | Oct-Mar
E | Identify goals and expectations for enrichment programming | Oct
E | Determine process for recruiting, selecting, and hiring enrichment partners and/or instructors, and if this process will be managed by the district, site leaders, and/or partners | Oct
E | Develop RFP to solicit enrichment partners (if applicable) including program information, application and contract process, and partner expectations (e.g. planning, operations, data-sharing, etc.) | Nov
E | Develop review rubric for evaluating proposals from prospective partners | Nov
E | Develop position descriptions and application for enrichment instructors | Nov
E | Disseminate RFP and/or position descriptions to prior partners and enrichment instructors | Dec
R | Reach out to promising organizations and/or individuals to encourage them to submit a proposal or apply | Dec
R | Establish committee to review proposals and/or applications (if applicable) | Dec
R | Receive and evaluate proposals and/or applications | Jan
E | Select partners and/or instructors (if applicable) | Jan
R | Receive approval of enrichment partners and/or instructors from district leadership or Board (if applicable) | Feb
E | Develop agreements or MOUs with providers that include roles, responsibilities, and resource allocation | Mar
Plan for quality enrichment |  | Jan-May
R | Identify goals and expectations for field trip experiences | Jan
E | Determine number of field trips and whether there will be a culminating event | Jan
E | Identify field trip locations | Feb
E | Confirm field trip schedule | Mar
E | Determine and secure transportation for field trips | Mar
R | Develop mechanism for providing enrichment providers with feedback about their programming | Mar
R | Hold a program orientation meeting with enrichment providers and review expectations for developing and submitting activity plans | Apr
E | Conduct background checks on non-district employees | Apr
R | Brief central office and site leadership staff on enrichment providers | Apr
E | Communicate expectations for staff roles on field trips and during culminating events | Apr
R | Hold facilities walk-through with enrichment partners | May
R | Collect activity plans from enrichment partners | May
R | Provide feedback on activity plans to enrichment partners | May
R | Invite families to field trips and culminating events, as appropriate | Jun
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Professional Development
SUMMER PLANNING CALENDAR WORKBOOK
PROFESSIONAL DEVELOPMENT
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 26.
Why professional development is important
High-quality staff are critical to maximizing student achievement and creating a positive program climate, but recruiting the right program leaders, teachers, staff, and enrichment providers is just the first step.
Success hinges on offering all staff and enrichment providers training and ongoing support to effectively use instructional time, support positive behaviors and relationships with students, reinforce program culture and values, and efficiently manage day-to-day operations.
How to get started
Begin by identifying the content areas that will need to be addressed in training, including program goals, curriculum and instruction, behavior management, site operating procedures, etc. Determine necessary training for enrichment partners. Set a schedule for professional development, considering other school-year district events or training to avoid conflicts for teachers and other staff.
Planning tips and recommendations
a Gain buy-in from district leadership on professional development plan.
a Ensure connection between professional development lead and curriculum lead so that professional development addresses critical components of curriculum, including differentiation and instructional strategies.
a Plan joint professional development sessions with academic teachers and enrichment staff.
a Include opportunities for all instructional staff to practice using curriculum, observe model lessons, and practice delivering the curriculum.
a Ensure enrichment partners receive training on the program's policies and operations, with a particular focus on the behavior management system.
a Facilitate professional development at least one week prior to the program start date.
a Ensure that professional development emphasizes the importance of maximizing instructional time.
a If available, share student data during professional development to inform instruction.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Plan professional development |  | Nov-Apr
E | Identify lead(s) and members of professional development planning team | Nov
E | Set schedule and topics for professional development planning meetings | Dec
E | Identify specific content for professional development for all instructional staff (teachers and enrichment providers), including curriculum, behavior management, and program policies and operations, and identify where outside expertise is needed | Jan
E | Develop professional development plan, including differentiation by staff roles | Feb
E | Identify professional development providers (if needed) | Feb
R | Confirm schedule for other district events to ensure professional development does not conflict with other trainings or activities | Feb
E | Confirm location and professional development logistics, including materials and technology needs | Mar
E | Share professional development schedule with sites | Mar
R | Develop plan for providing instructional support once the program begins | Apr
Implement Professional Development |  | May-Jun
E | Provide orientation and training for all professional development providers, including teachers and instructional staff who will lead components of site-level trainings | May
E | Deliver materials necessary for professional development to training sites, including curriculum, lesson plans, program policies or handbooks, etc. | Jun
E | Conduct professional development on curriculum for all teachers | Jun
R | Hold site-level orientation for all staff (academic and enrichment) to review and discuss site logistics, culture and climate, behavior system, and operating procedures | Jun
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Site Operations and Culture
SUMMER PLANNING CALENDAR WORKBOOK
SITE OPERATIONS AND CULTURE
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 26.
Why site operations and culture are important
In Getting to Work on Summer Learning, 2nd ed., RAND researchers emphasize that site management directly influences the daily experiences and learning of students.
Setting policies and procedures with clear expectations and protocols for staff and student attendance, behavior management, and program culture and climate help reduce site disorganization that can disrupt instructional time. To make sure everyone is on the same page, program leaders should articulate standards to staff and families through program communications, manuals, trainings, and orientations.
How to get started
Begin by considering program goals and values to define the culture and climate you want to create for your program. Explore how day-to-day operations and expectations for student and staff engagement can support that climate and how you can encourage those standards through policies, procedures, and program incentives.
Planning tips and recommendations
a Assign responsibilities for developing and overseeing policies and procedures related to attendance, behavior, and culture to the district or individual sites. Or, assign shared responsibility, depending on the program model.
a Provide teachers and enrichment partners with a discipline action flow chart.
a Ensure that both teachers and enrichment partners receive training on behavior management.
a Identify opportunities to incorporate youth voice and leadership into program planning and throughout the summer.
a Identify ways to incorporate program culture through décor, rituals and traditions, and field trips.
a Consider establishing program principles and an overarching program theme to communicate program values and aspirations and build a warm and caring environment.
a Communicate policies and procedures to staff through program manuals, professional development, and site-level orientation.
a For sites operating co-located programs, consider establishing site-wide policies when possible to mitigate conflicts or disruptions between programs. Provide program leaders with information on all co-located programs including schedules and program-specific policies and procedures.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Define program culture and operating policies and procedures |  | Nov-Feb
E | Develop or update student and staff attendance policies | Nov
E | Define expectations for program culture and classroom climate that communicate program values and aspirations | Dec
R | Develop or update behavior management policies that include expectations, infractions, and steps staff should take for each level of infraction | Jan
R | Develop or update student attendance incentive plan | Jan
R | Update and finalize program manual | Feb
Prepare site management procedures |  | Feb-Jun
E | Coordinate with IT to develop or adapt school-year tracking systems for the summer program | Feb
E | Develop process to submit daily attendance | Mar
E | Share student attendance tracking process and behavior management procedures with site leadership, if applicable | Apr
R | Assign one person per site to oversee implementation of behavior management procedures | Apr
E | Use student rosters to create attendance tracking system | May
R | Produce materials and décor to brand program space | May
E | Coordinate process for collecting health forms in collaboration with school-year nurses and/or district personnel in charge of oversight | May
E | Develop process for tracking staff attendance and hourly payroll | May
E | Review all operating policies and procedures during staff professional development and onsite orientation | Jun
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Schedules & Rosters
SUMMER PLANNING CALENDAR WORKBOOK
SCHEDULES AND ROSTERS
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 22.
Why schedules and rosters are important
A successful day in a summer program, one where staff and students accomplish all they have set out to do, is dependent upon buses arriving on time, classes starting and ending on time, students and teachers knowing where to go, and meals being provided as planned. If not properly planned and staffed, daily transitions for meals, bathroom breaks, and class rotations can disrupt the program schedule and take away critical time for instruction and enrichment.
Site schedules create routines for staff and students that enable them to focus less on logistics and more on learning and enrichment. Class and student rosters also help site leaders locate students and staff quickly if needed.
How to get started
Begin by determining the balance of academic and enrichment instruction that needs to be provided daily to meet your program goals. Next, consider the culture and climate you want to create and how you will build in daily activities and rituals to support building an engaging program culture. Consider the layout of your facility and the time needed for students to move between activities throughout the day to ensure appropriate time for breaks and transitions.
Planning tips and recommendations
a Schedule classes to occur in one continuous block to ensure transitions, lunch, snack, and special events do not break up or take away from academic instruction.
a Include bathroom breaks in the site schedule.
a Consider activity needs (e.g. A/V, access to outdoors, air conditioning, etc.) when identifying program rooms and spaces.
a Consider the distance between all program areas and key amenities (e.g. bathrooms) and group sequential activities in similar areas to minimize transition time and disruptions.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Develop program schedule |  | Nov
E | Develop program schedule, including start and end dates and overall program structure with appropriate time for academic instruction | Nov
Develop and share site schedules |  | Jan, Mar-Apr
E | Develop consistent daily schedule including time for transitions and breaks | Jan
E | Assign rooms and program spaces for all classes and enrichment activities | Mar
E | Share site schedules with site leaders and teachers | Apr
E | Share program schedule with students and families | Apr
Develop and share class schedules |  | May-Jun
R | Complete student groupings based on academic needs and enrichment interests | May
R | Develop classroom-level schedules for students within a group or class | May
E | Provide class rosters to site leaders and teachers | Jun
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Transportation
SUMMER PLANNING CALENDAR WORKBOOK
TRANSPORTATION
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 22.
Why transportation planning is important
Ensuring smooth and efficient transportation for students to and from the program is critical to program success. Late arrivals increase disorganization at the site and disrupt important instructional time. Most summer programs operate an average of 25-30 days, so you can’t afford to lose even a day to transportation issues. It’s important to test-run your routes prior to the program’s first day. Additionally, providing families with clear information about the schedule and location for their pick-up, and reminders up to the first day, helps make sure every student has an easy first day.
How to get started
Begin by determining all of your transportation needs, including feeder patterns, anticipated number of students per site, offsite program field trips, and accommodations for students with special needs. Consider your program schedule to set arrival and departure times.
Planning tips and recommendations
✓ Coordinate a practice run prior to the start of the program to ensure smooth pick-ups and arrivals on the first day.
✓ Coordinate with appropriate departments to identify students in need of door-to-door transportation.
✓ Ensure that every student is included on a bus route or is noted as a walker.
✓ Ensure that operations managers are equipped to respond to parent calls regarding transportation.
✓ Develop a systematic way to share transportation information with families such as specific mailers and robo calls.
✓ Re-confirm transportation schedule for field trips with vendor prior to each offsite activity.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Coordinate transportation |  | Nov, Jan-Apr
R | Hold initial planning meeting with transportation department to debrief the prior summer's program and establish communication and coordination plans for the upcoming summer | Nov
E | Determine transportation needs including transporting students to and from the program, field trips, and other events | Jan
E | If applicable, secure transporation vendor | Feb
R | Designate a site leader to manage transportation for each entire site | Feb
E | Identify appropriate pick-up and drop-off locations | Mar
E | Meet with transportation department or vendor to begin scheduling routes and determining cost estimates | Mar
E | Develop a process for arrivals and dismissals at each site | Mar
E | Arrange field trip transportation | Apr
E | Finalize transportation master plan | Apr
Execute transportation |  | May-Aug
E | Receive bus routes from transportation department or vendor | May
R | Conduct transportation test run | May
E | Provide transportation routes to site leaders | Jun
E | Provide student roster for each site to transportation department or vendor | Jun
E | Oversee transportation and troubleshoot challenges as needed | Jun-Aug
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Meals
SUMMER PLANNING CALENDAR WORKBOOK
MEALS
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 18.
Why meal planning is important
A summer meals plan includes projecting and preparing for food delivery, preparation, and service across all sites. Individual site plans ensure smooth program operations and minimize delays or disruptions to instructional time.
How to get started
In early winter, predict student numbers for each site and meet with the food services department to discuss logistics. Once you’ve established program schedules and confirmed enrollment capacity, begin working on the detailed service plan for each site.
Planning tips and recommendations
✓ Consider attrition within project enrollment and use historic average daily attendance rates (ADA) to more accurately project number of anticipated students at each site; if you don’t have historic data, assume a 75% ADA.
✓ Review program schedule to confirm that meal and snack times do not break up instructional blocks.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Coordinate food service |  | Nov, Jan-Feb
R | Hold initial planning meeting with food services team to debrief prior summer program and establish communication and coordination plan for upcoming summer | Nov
E | Provide food service department with school locations and projections for each site | Jan
E | Hold planning meeting with food services team to review summer program plans including number and location of sites, number of anticipated students at each site, meal times, etc. | Feb
E | Finalize food service master plan | Feb
Coordinate and execute food service at each summer program site |  | Mar, May-Jun
E | Establish meal times for each site | Mar
E | Secure and review draft menus to confirm meal plan | May
E | Distribute final menus to sites | Jun
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Supplies
SUMMER PLANNING CALENDAR WORKBOOK
SUPPLIES
INSTRUCTIONS
For more information about how to use this worksheet, collapse or expand instruction panel using the ( + ) or ( - ) symbol in the left margin next to row 19.
Why supply planning is important
Districts often have limited time between when the school year ends and the summer program begins. An organized approach for ordering, distributing, and managing supplies at individual sites helps site leaders and teachers quickly prepare and kick off the program with everything they need.
How to get started
Begin by going through the curriculum and program schedule (including field trips) to brainstorm all the supplies and materials that are necessary to operate the program. Then, compare existing inventory with needs to determine gaps. Plan to order supplies 2-3 months prior to the program launch and store everything centrally.
Planning tips and recommendations
✓ Ensure your supply list includes basic building supplies, custodial supplies, and nursing supplies.
✓ Ensure supplies are delivered at least one week prior to start of the program.
✓ If the summer site leader is different than during the school year, wait until the summer leader is onsite to deliver supplies.
* use three-letter abbreviation for month, no periods (this column is aggregated and sortable in the last sheet) † to change drop-down options for APPROVAL REQUIRED and STATUS, scroll down to the blue section below this table
KEY ACTIVITIES & TASKS |  | RECOMMENDED TIMELINE | OUR TIMELINE* | WHO'S RESPONSIBLE? | APPROVAL REQUIRED† | IF APPROVAL REQUIRED, BY WHOM? | DEADLINE (M/DD/YY) | STATUS* | DATE COMPLETED | NOTES (Planning Dependencies, Challenges, or Delays)
Determine supply needs |  | Jan-Feb
E | Determine supply needs by reviewing plans, surveying staff from previous years, and checking against curricular, enrichment, and field trip needs | Jan
E | Complete an inventory of existing supplies | Jan
E | Ask central office and site leadership for additional supply requests | Feb
E | Prepare supply orders | Feb
Order, organize and deliver supplies to sites |  | Mar-Jun
E | Order supplies | Mar
R | Develop schedule for distribution | Mar
E | Determine where supplies will be stored at sites prior to program launch | Mar
E | Provide site leadership with materials list and distribution instructions | Apr
E | Inventory materials and supplies to ensure all ordered supplies were received | Apr
E | Organize supplies for site distribution | May
E | Deliver supplies to all sites | Jun
Manage supplies during and after the program |  | May-Jun, Aug
E | Determine process for purchasing necessary supplies during the summer program | May
R | Provide technology and equipment inventory for site leaders and principals to develop process for check out and return | May
R | Develop process for end-of-summer supply return and inventory | Jun
E | Collect and inventory supplies at the end of the program | Aug
KEY
E | Essential Task
R | Recommended Task
| EDIT DROP-DOWN OPTIONS | Column F: APPROVAL REQUIRED | Column I: STATUS
| You may edit the list of APPROVAL and STATUS | Yes | Not started
| drop-down options using the white cells to the right. | No | In progress
Pending approval
| ADD STATUS TYPES |  | Completed
You can add other status types in the yellow cells to the right. Once added, they will appear in the drop-down for STATUS.

## Sortable Task List
SUMMER PLANNING CALENDAR WORKBOOK
SORTABLE TASK LIST
INSTRUCTIONS FOR SORTING
You can click the down arrow to filter or to sort any column alphabetically. To sort OUR TIMELINE chronologically, click the down arrow in the header, then the right arrow next to Sort by Color. Select Custom Sort. In the pop up box, make sure it's set to Sort by 'Our Timeline,' Sort on 'Cell Values,' and Order 'Sep, Oct, Nov...'. Click OK. NOTE: For the sort to function properly, you must use the three-letter abbreviation for month (with no periods) in the OUR TIMELINE columns on all other sheets.
CATEGORY | TASK | OUR TIMELINE | ESSENTIAL / RECOMMENDED | DEADLINE | STATUS | DATE COMPLETED
CONTINUOUS IMPROVEMENT PROCESS | Define or update program goals and expected outcomes | 0 | R | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Identify lead(s) and members of professional development planning team | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Identify specific content for professional development for all instructional staff (teachers and enrichment providers), including curriculum, behavior management, and program policies and operations, and identify where outside expertise is needed | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Observe academic and enrichment instruction and provide feedback to staff during and at the end of the program | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Begin to discuss the evaluation plan for next summer | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Finalize the program evaluation plan, including systems and processes for data collection, analysis, dissemination, and application | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Share end-of-summer data from previous summer with program stakeholders | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Collect spring reading and math data to form class groupings by ability levels | 0 | R | 0 |  | 0
CONTINUOUS IMPROVEMENT PROCESS | Provide data in an easily accessible format to classroom teachers | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Collect and analyze fall student testing data and compare to previous spring testing data to assess student and program outcomes from the previous summer program | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Administer pre-assessments according to schedule (e.g. spring school-year assessments or in-program skills pre-assessment) | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Conduct end-of-program assessment (if applicable) | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Conduct focus groups to gather feedback from key stakeholders including students, families, staff, and partners | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Begin to prepare end-of-summer data reports on enrollment, attendance, program quality, student outcomes, and satisfaction surveys (staff, student, families, and partners) for various stakeholder groups, including principals | 0 | R | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Determine data sharing requirements and include relevant language in partner MOUs | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Select or develop assessments to measure program quality and student outcomes (e.g. youth academic and social emotional skills; instructional quality; effectiveness of professional development; and participant, staff, and stakeholder satisfaction, etc.) | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Develop mechanism to monitor fidelity of curriculum and enrichment implementation | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Conduct debrief with planning team and examine data from previous summer to identify improvements for next summer | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Collect and analyze student daily attendance data | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Analyze collected data | 0 | E | 0 | 0 | 0
CONTINUOUS IMPROVEMENT PROCESS | Develop list of students that met promotion criteria (if applicable) | 0 | E | 0 | 0 | 0
CURRICULUM | Review commercially available and evidence-based curriculum and determine if curriculum aligned with program goals needs to be selected, developed, or revised | 0 | R | 0 | 0 | 0
CURRICULUM | If program requires use of specific student assessment data for grouping or instructional purposes, schedule pre-assessment prior to program launch | 0 | R | 0 | 0 | 0
CURRICULUM | Review student achievement data (winter benchmark) to determine student needs, including remediation | 0 | R | 0 | 0 | 0
CURRICULUM | Draft or revise pacing guides and lesson plans to provide sufficient guidance to teachers | 0 | R | 0 | 0 | 0
CURRICULUM | Finalize pacing guides and lesson plans to address district-specific decisions and needs related to groupings, differentiation, instruction for students with IEP's, etc. | 0 | R | 0 | 0 | 0
CURRICULUM | Set program goals for student outcomes | 0 | E | 0 | 0 | 0
CURRICULUM | Identify staff to lead curriculum process | 0 | E | 0 | 0 | 0
CURRICULUM | Request and provide curriculum team with first quarter reading and math data to assess student needs | 0 | E | 0 | 0 | 0
CURRICULUM | If curriculum is computer-based, engage IT to identify technology needs and coordinate support leading up to and throughout the program | 0 | E | 0 | 0 | 0
CURRICULUM | Complete an inventory of available curriculum materials and determine what is still needed for the program | 0 | E | 0 | 0 | 0
CURRICULUM | Order additional materials and supplies | 0 | E | 0 | 0 | 0
CURRICULUM | Print and prepare program-developed curriculum (e.g. lesson plans) | 0 | E | 0 | 0 | 0
CURRICULUM | Organize all materials for easy pick-up and use | 0 | E | 0 | 0 | 0
ENRICHMENT | Reach out to promising organizations and/or individuals to encourage them to submit a proposal or apply | 0 | R | 0 | 0 | 0
ENRICHMENT | Establish committee to review proposals and/or applications (if applicable) | 0 | R | 0 | 0 | 0
ENRICHMENT | Receive and evaluate proposals and/or applications | 0 | R | 0 | 0 | 0
ENRICHMENT | Receive approval of enrichment partners and/or instructors from district leadership or Board (if applicable) | 0 | R | 0 | 0 | 0
ENRICHMENT | Identify goals and expectations for field trip experiences | 0 | R | 0 | 0 | 0
ENRICHMENT | Develop mechanism for providing enrichment providers with feedback about their programming | 0 | R | 0 | 0 | 0
ENRICHMENT | Hold a program orientation meeting with enrichment providers and review expectations for developing and submitting activity plans | 0 | R | 0 | 0 | 0
ENRICHMENT | Brief central office and site leadership staff on enrichment providers | 0 | R | 0 | 0 | 0
ENRICHMENT | Hold facilities walk-through with enrichment partners | 0 | R | 0 | 0 | 0
ENRICHMENT | Collect activity plans from enrichment partners | 0 | R | 0 | 0 | 0
ENRICHMENT | Provide feedback on activity plans to enrichment partners | 0 | R | 0 | 0 | 0
ENRICHMENT | Invite families to field trips and culminating events, as appropriate | 0 | R | 0 | 0 | 0
ENRICHMENT | Identify goals and expectations for enrichment programming | 0 | E | 0 | 0 | 0
ENRICHMENT | Determine process for recruiting, selecting, and hiring enrichment partners and/or instructors, and if this process will be managed by the district, site leaders, and/or partners | 0 | E | 0 | 0 | 0
ENRICHMENT | Develop RFP to solicit enrichment partners (if applicable) including program information, application and contract process, and partner expectations (e.g. planning, operations, data-sharing, etc.) | 0 | E | 0 | 0 | 0
ENRICHMENT | Develop review rubric for evaluating proposals from prospective partners | 0 | E | 0 | 0 | 0
ENRICHMENT | Develop position descriptions and application for enrichment instructors | 0 | E | 0 | 0 | 0
ENRICHMENT | Disseminate RFP and/or position descriptions to prior partners and enrichment instructors | 0 | E | 0 | 0 | 0
ENRICHMENT | Select partners and/or instructors (if applicable) | 0 | E | 0 | 0 | 0
ENRICHMENT | Develop agreements or MOUs with providers that include roles, responsibilities, and resource allocation | 0 | E | 0 | 0 | 0
ENRICHMENT | Determine number of field trips and whether there will be a culminating event | 0 | E | 0 | 0 | 0
ENRICHMENT | Identify field trip locations | 0 | E | 0 | 0 | 0
ENRICHMENT | Confirm field trip schedule | 0 | E | 0 | 0 | 0
ENRICHMENT | Determine and secure transportation for field trips | 0 | E | 0 | 0 | 0
ENRICHMENT | Conduct background checks on non-district employees | 0 | E | 0 | 0 | 0
ENRICHMENT | Communicate expectations for staff roles on field trips and during culminating events | 0 | E | 0 | 0 | 0
FACILITIES | Develop a list of targeted sites to host summer programs | 0 | R | 0 | 0 | 0
FACILITIES | Create a preliminary projection of the number of students that will attend each site | 0 | R | 0 | 0 | 0
FACILITIES | Develop written agreement that describes how the sites will be used | 0 | R | 0 | 0 | 0
FACILITIES | Conduct meetings between summer site principals and school-year principals to discuss facility needs, emergency plans, bus drop-off locations, etc. | 0 | R | 0 | 0 | 0
FACILITIES | Conduct site walk-throughs | 0 | R | 0 | 0 | 0
FACILITIES | Develop safety plan for summer site principals to share with staff during professional development | 0 | R | 0 | 0 | 0
FACILITIES | Meet with directors of facilities and custodial services to review building capacity and capital improvements or construction planned for the summer | 0 | E | 0 | 0 | 0
FACILITIES | Research city and school district summer permitting processes, if applicable | 0 | E | 0 | 0 | 0
FACILITIES | Confirm dates for summer program based on school calendar and facilities availability | 0 | E | 0 | 0 | 0
FACILITIES | Confirm sites and available classrooms for summer program | 0 | E | 0 | 0 | 0
FACILITIES | Identify contacts for facilities, equipment, etc., at each site | 0 | E | 0 | 0 | 0
FACILITIES | Notify school-year principals of site selection and requirements for hosting summer program | 0 | E | 0 | 0 | 0
FACILITIES | Determine feeder patterns, if applicable | 0 | E | 0 | 0 | 0
FACILITIES | Coordinate with the district (and/or city if appropriate) to ensure that school zones operate during the summer and that crossing guards are available at all locations | 0 | E | 0 | 0 | 0
MEALS | Hold initial planning meeting with food services team to debrief prior summer program and establish communication and coordination plan for upcoming summer | 0 | R | 0 | 0 | 0
MEALS | Provide food service department with school locations and projections for each site | 0 | E | 0 | 0 | 0
MEALS | Hold planning meeting with food services team to review summer program plans including number and location of sites, number of anticipated students at each site, meal times, etc. | 0 | E | 0 | 0 | 0
MEALS | Finalize food service master plan | 0 | E | 0 | 0 | 0
MEALS | Establish meal times for each site | 0 | E | 0 | 0 | 0
MEALS | Secure and review draft menus to confirm meal plan | 0 | E | 0 | 0 | 0
MEALS | Distribute final menus to sites | 0 | E | 0 | 0 | 0
PLANNING AND MANGEMENT | Confirm staff lead to oversee summer program planning | 0 | E | 0 | 0 | 0
PLANNING AND MANGEMENT | Define roles and responsibilities for district, site leadership, and partner staff related to program planning and implementation | 0 | E | 0 | 0 | 0
PLANNING AND MANGEMENT | Develop system to coordinate and track planning progress | 0 | E | 0 | 0 | 0
PLANNING AND MANGEMENT | Determine members of planning team | 0 | E | 0 | 0 | 0
PLANNING AND MANGEMENT | Develop monthly planning schedule with key tasks, monthly deadlines, and who's responsible (including district, site leadership, and partner staff) | 0 | R | 0 | 0 | 0
PLANNING AND MANGEMENT | Identify planning expectations (responsibilities, meeting schedule) for all staff to include in job descriptions | 0 | R | 0 | 0 | 0
PLANNING AND MANGEMENT | Identify planning expectations (responsibilities, meeting schedule) for all partners to include in partner agreements | 0 | R | 0 | 0 | 0
PLANNING AND MANGEMENT | Collect feedback on the delineation of roles and responsibilities for planning, program management, and evaluation during annual debrief with district staff, site leadership, and partners | 0 | R | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Share professional development schedule with sites | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Confirm schedule for other district events to ensure professional development does not conflict with other trainings or activities | 0 | R | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Develop plan for providing instructional support once the program begins | 0 | R | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Hold site-level orientation for all staff (academic and enrichment) to review and discuss site logistics, culture and climate, behavior system, and operating procedures | 0 | R | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Set schedule and topics for professional development planning meetings | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Develop professional development plan, including differentiation by staff roles | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Identify professional development providers (if needed) | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Confirm location and professional development logistics, including materials and technology needs | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Provide orientation and training for all professional development providers, including teachers and instructional staff who will lead components of site-level trainings | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Deliver materials necessary for professional development to training sites, including curriculum, lesson plans, program policies or handbooks, etc. | 0 | E | 0 | 0 | 0
PROFESSIONAL DEVELOPMENT | Conduct professional development on curriculum for all teachers | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Schedule regular meetings with finance or other administration to periodically review budgets | 0 | R | 0 | 0 | 0
PROGRAM BUDGET | Identify potential funding sources to support program growth and sustainability | 0 | R | 0 | 0 | 0
PROGRAM BUDGET | Prepare fundraising materials including case statements, proposals, budgets, impact data, etc. | 0 | R | 0 | 0 | 0
PROGRAM BUDGET | Confirm new funding, update budgets and revenue sources, and develop plan for managing funding based on requirements | 0 | R | 0 | 0 | 0
PROGRAM BUDGET | Estimate budget based on prior year budget and actual expenditures | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Determine primary costs for each site including personnel, facilities, meals, transportation, materials and supplies, and administrative and overhead costs | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Discuss budget estimates with district leadership | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Confirm existing federal, state, local, district, and philanthropic funds that will support the program | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Identify revenue gaps and operating categories that require additional funding | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Present draft budget to district leadership for approval | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Confirm budget to operate each summer site and update budget draft | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Engage the leadership planning team to review the updated draft budget | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Finalize program budget | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Develop payment process for enrichment partners and vendors | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Develop process to manage and track expenditures against budget | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Process final expenses and payments | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Reconcile all expenditures against budget | 0 | E | 0 | 0 | 0
PROGRAM BUDGET | Prepare financial reports for district/community leaders and program funders | 0 | E | 0 | 0 | 0
SCHEDULES AND ROSTERS | Complete student groupings based on academic needs and enrichment interests | 0 | R | 0 | 0 | 0
SCHEDULES AND ROSTERS | Develop classroom-level schedules for students within a group or class | 0 | R | 0 | 0 | 0
SCHEDULES AND ROSTERS | Develop program schedule, including start and end dates and overall program structure with appropriate time for academic instruction | 0 | E | 0 | 0 | 0
SCHEDULES AND ROSTERS | Develop consistent daily schedule including time for transitions and breaks | 0 | E | 0 | 0 | 0
SCHEDULES AND ROSTERS | Assign rooms and program spaces for all classes and enrichment activities | 0 | E | 0 | 0 | 0
SCHEDULES AND ROSTERS | Share site schedules with site leaders and teachers | 0 | E | 0 | 0 | 0
SCHEDULES AND ROSTERS | Share program schedule with students and families | 0 | E | 0 | 0 | 0
SCHEDULES AND ROSTERS | Provide class rosters to site leaders and teachers | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Develop or update behavior management policies that include expectations, infractions, and steps staff should take for each level of infraction | 0 | R | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Develop or update student attendance incentive plan | 0 | R | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Update and finalize program manual | 0 | R | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Assign one person per site to oversee implementation of behavior management procedures | 0 | R | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Produce materials and décor to brand program space | 0 | R | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Develop or update student and staff attendance policies | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Define expectations for program culture and classroom climate that communicate program values and aspirations | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Coordinate with IT to develop or adapt school-year tracking systems for the summer program | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Develop process to submit daily attendance | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Share student attendance tracking process and behavior management procedures with site leadership, if applicable | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Use student rosters to create attendance tracking system | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Coordinate process for collecting health forms in collaboration with school-year nurses and/or district personnel in charge of oversight | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Develop process for tracking staff attendance and hourly payroll | 0 | E | 0 | 0 | 0
SITE OPERATIONS AND CULTURE | Review all operating policies and procedures during staff professional development and onsite orientation | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Coordinate hiring process with district staff who manage payroll and district hiring system | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Negotiate, update and sign union MOU that describes requirements of teachers and staff and the selection and hiring process | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Develop process for tracking candidates and re-staffing position vacancies from waiting list (if/when need arises) | 0 | R | 0 | 0 | 0
STAFFING AND HIRING | Identify and connect with staff from prior years who are encouraged to return | 0 | R | 0 | 0 | 0
STAFFING AND HIRING | Identify and connect with staff from prior years who are encouraged to return | 0 | R | 0 | 0 | 0
STAFFING AND HIRING | Identify and connect with staff from prior years who are encouraged to return | 0 | R | 0 | 0 | 0
STAFFING AND HIRING | Define roles and responsibilities for site-level leadership related to program planning and implementation | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Determine staffing needs for instructional positions and additional staff (e.g., classroom support, special education, nurses, custodians, etc.) | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Determine hiring timeline for key positions including seasonal central office staff, site leadership, and teachers | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Develop hiring and selection process for central office and site leadership, including application requirements and review rubric | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Establish rate of pay for all summer program staff, including stipends for participation in professional development | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Develop hiring and selection process for teachers, including application requirements and review rubric | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Develop hiring and selection process for additional staff including application requirements and review rubric | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Develop job descriptions for site leads | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Promote positions to eligible staff through district communication vehicles and personalized outreach | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Review applications | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Interview top candidates | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Make offers and secure commitments | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Develop job descriptions for seasonal central office staff | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Promote positions to eligible staff through district communication vehicles and personalized outreach | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Review applications | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Interview top candidates | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Make offers and secure commitments | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Review teacher applications | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Interview top candidates for teaching positions | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Make selection decisions, including assigning teachers to schools, subject areas, and grade levels according to experience | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Make offers and secure commitments from selected teachers | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Meet with district departments regarding additional staffing needs to identify positions and select staff (e.g. health services, food service, etc.) | 0 | E | 0 | 0 | 0
STAFFING AND HIRING | Manage the process for confirming staff for these positions | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Close registration | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Maintain waiting list and notify parents of enrollment if applicable | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Identify all audiences with whom you need to communicate (e.g. priority families and students for recruitment) | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Identify strategies for successfully reaching each of your target audiences | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Develop a timeline for all outreach and recruitment activities | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Develop strategies to measure success | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Develop student identification plan including eligibility requirements | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Develop recruitment packages for staff who play an essential role in outreach and recruitment (e.g., registration and outreach materials for planned family communications, such as mailers, talking points for outreach calls, personalized outreach, etc.) | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Begin registration | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Send second communication home with registration deadline reminder | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Utilize test results to identify students who will be mandated to attend summer school for grade promotion (if applicable) | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Make final reminder calls to families immediately prior to the program launch | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Call parents of registered students who have not shown up to remind them of the program | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Send mid-program newsletter to families | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Send notification or reminder about culminating event(s) to families | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Send thank you letters to students and families | 0 | R | 0 | 0 | 0
STUDENT RECRUITMENT | Determine enrollment process | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Create engaging messaging | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Develop enrollment and consent forms and translate materials into appropriate languages | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Train school staff (e.g. attendance clerks) on process to manage summer enrollment on site | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Announce summer program dates | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Equip messengers, including providing information on enrollment process to school principals | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Update school website with summer program information | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Send first communication home with information on registration process and deadline | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Distribute registration materials to schools | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Equip teachers or other designated recruitment specialists to conduct individualized outreach to eligible students and families | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Facilitate phone calls to homes (robocalls or personalized) | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Facilitate final reminder calls to families who have not registered yet (robocalls or personalized) | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Send confirmation letters or postcards to families and students who enrolled, notifying them that their spot has been reserved | 0 | E | 0 | 0 | 0
STUDENT RECRUITMENT | Share behavior management policy, attendance expectations and incentives, and transportation schedule with students and families through pre-program mailer | 0 | E | 0 | 0 | 0
SUPPLIES | Develop schedule for distribution | 0 | R | 0 | 0 | 0
SUPPLIES | Provide technology and equipment inventory for site leaders and principals to develop process for check out and return | 0 | R | 0 | 0 | 0
SUPPLIES | Develop process for end-of-summer supply return and inventory | 0 | R | 0 | 0 | 0
SUPPLIES | Determine supply needs by reviewing plans, surveying staff from previous years, and checking against curricular, enrichment, and field trip needs | 0 | E | 0 | 0 | 0
SUPPLIES | Complete an inventory of existing supplies | 0 | E | 0 | 0 | 0
SUPPLIES | Ask central office and site leadership for additional supply requests | 0 | E | 0 | 0 | 0
SUPPLIES | Prepare supply orders | 0 | E | 0 | 0 | 0
SUPPLIES | Order supplies | 0 | E | 0 | 0 | 0
SUPPLIES | Determine where supplies will be stored at sites prior to program launch | 0 | E | 0 | 0 | 0
SUPPLIES | Provide site leadership with materials list and distribution instructions | 0 | E | 0 | 0 | 0
SUPPLIES | Inventory materials and supplies to ensure all ordered supplies were received | 0 | E | 0 | 0 | 0
SUPPLIES | Organize supplies for site distribution | 0 | E | 0 | 0 | 0
SUPPLIES | Deliver supplies to all sites | 0 | E | 0 | 0 | 0
SUPPLIES | Determine process for purchasing necessary supplies during the summer program | 0 | E | 0 | 0 | 0
SUPPLIES | Collect and inventory supplies at the end of the program | 0 | E | 0 | 0 | 0
TRANSPORTATION | Hold initial planning meeting with transportation department to debrief the prior summer's program and establish communication and coordination plans for the upcoming summer | 0 | R | 0 | 0 | 0
TRANSPORTATION | Designate a site leader to manage transportation for each entire site | 0 | R | 0 | 0 | 0
TRANSPORTATION | Conduct transportation test run | 0 | R | 0 | 0 | 0
TRANSPORTATION | Determine transportation needs including transporting students to and from the program, field trips, and other events | 0 | E | 0 | 0 | 0
TRANSPORTATION | If applicable, secure transporation vendor | 0 | E | 0 | 0 | 0
TRANSPORTATION | Identify appropriate pick-up and drop-off locations | 0 | E | 0 | 0 | 0
TRANSPORTATION | Meet with transportation department or vendor to begin scheduling routes and determining cost estimates | 0 | E | 0 | 0 | 0
TRANSPORTATION | Develop a process for arrivals and dismissals at each site | 0 | E | 0 | 0 | 0
TRANSPORTATION | Arrange field trip transportation | 0 | E | 0 | 0 | 0
TRANSPORTATION | Finalize transportation master plan | 0 | E | 0 | 0 | 0
TRANSPORTATION | Receive bus routes from transportation department or vendor | 0 | E | 0 | 0 | 0
TRANSPORTATION | Provide transportation routes to site leaders | 0 | E | 0 | 0 | 0
TRANSPORTATION | Provide student roster for each site to transportation department or vendor | 0 | E | 0 | 0 | 0
TRANSPORTATION | Oversee transportation and troubleshoot challenges as needed | 0 | E | 0 | 0 | 0

## Planning and Operations Dashboa
ADSY PEP SUMMER LEARNING WORK PLAN
PLANNING AND OPERATIONS DASHBOARD
INSTRUCTIONS FOR SORTING
This worksheet will automatically update based on udates made to the individual task category tabs. Updates CANNOT be made from this tab. You can sort this comprehensive task list by selecting the sort column in cell B6 and selecting the corresponding equation from cell C6. If the task list does not appear to be sorting correctly, check cell C6 for a small red tag in the top right corner of the cell. This indicates that the sort equation has not been updated to match your selected Sort By column. NOTE: For the sort to function properly, you must use the 4-digit year followed by the three-letter abbreviation for month (with no periods) in the OUR TIMELINE columns on all other sheets.
Sort By | EssentialRecommended | SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col2
The Sortable Task List is built using QUERY function. Do not edit the functions below.
FUNCTION | Category | OurTimeline | EssentialRecommended | Deadline | WhosResponsible | Status | DateCompleted
SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col2 | SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col1 | SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col5 | SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col2 | SELECT Col1, Col3, Col5, Col2, Col9, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col9 | SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col6 | SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col10 | SELECT Col1, Col3, Col5, Col2, Col9, Col6, Col10, Col11 WHERE Col3 IS NOT NULL ORDER BY Col12
CATEGORY | TASK | OUR TIMELINE | ESSENTIAL / RECOMMENDED | DEADLINE | WHO'S RESPONSIBLE? | STATUS | DATE COMPLETED
#VALUE!